## Project schedule
| TurboRent | [5 empty] | Project start: | [7 empty] | 2024-09-02
| Fullstack - Kelemen Balázs János | [5 empty] | Display week: | [7 empty] | 1
Backend - Pidl Ádám
| Database - Bata Dániel Tamás | [5 empty] | 2024-09-02 | [6 empty] | 2024-09-09 | [6 empty] | 2024-09-16 | [6 empty] | 2024-09-23 | [6 empty] | 2024-09-30 | [6 empty] | 2024-10-07 | [6 empty] | 2024-10-14 | [6 empty] | 2024-10-21 | [6 empty] | 2024-10-28 | [6 empty] | 2024-11-04 | [6 empty] | 2024-11-11 | [6 empty] | 2024-11-18 | [6 empty] | 2024-11-25 | [6 empty] | 2024-12-02 | [6 empty] | 2024-12-09 | [6 empty] | 2024-12-16 | [6 empty] | 2024-12-23 | [6 empty] | 2024-12-30
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2024-09-02 to 2025-01-05
 | time axis 2024-09-02 to 2025-01-05
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Frontend - Kelemen Balázs
| Figma design | Kelemen Balázs János | 100% | 2024-09-02 | 2024-09-15 | 14
| Designing components | Kelemen Balázs János | 100% | 2024-09-16 | 2024-11-22 | 68
| Comunication with backend w/ Angular Services | Kelemen Balázs János | 100% | 2024-09-28 | 2024-10-11 | 14
| Contact Form & allowing contact with support | Kelemen Balázs János | 100% | 2024-10-21 | 2024-11-16 | 27
| Login & Register form | Kelemen Balázs János | 100% | 2024-11-06 | 2024-11-14 | 9
| Dashboard & Dashboard functions | Kelemen Balázs János | 100% | 2024-10-01 | 2024-12-06 | 67
| Renting 101 & Renting functions | Kelemen Balázs János | 100% | 2024-10-21 | 2024-11-07 | 18
Backend - Pidl Ádám
| Backend, using NodeJS & ExpressJS | Pidl Ádám | 100% | 2024-09-02 | 2024-10-07
| MySQL pools & connections | Pidl Ádám | 100% | 2024-09-05 | 2024-09-12 | 8
| API Requests | Pidl Ádám | 100% | 2024-09-02 | 2024-10-03 | 32
| Migrating requests to Postman | Pidl Ádám | 100% | 2024-10-03 | 2024-10-12 | 10
| Test cases | Pidl Ádám | 100% | 2024-11-12 | 2024-11-28 | 17
Database - Bata Dániel
| Database plan | Bata Dániel Tamás | 100% | 2024-09-10 | 2024-09-11 | 2
| Database tables | Bata Dániel Tamás | 100% | 2024-09-13 | 2024-11-22 | 71
| Filling tables up with dummy data | Bata Dániel Tamás | 100% | 2024-10-02 | 2024-11-05 | 35
| Procedures | Bata Dániel Tamás | 100% | 2024-09-13 | 2024-11-02 | 51
| Documentations regarding to the project | Bata Dániel Tamás | 100% | 2024-11-27 | 2025-04-14 | 139